## DocProc Status
Category | Task | Status
Core Infrastructure | Create Function App (docproc-ingest-fn) | Done
Core Infrastructure | Create Function App Storage Account | Done
Core Infrastructure | Create Application Insights | Done
Core Infrastructure | Enable Managed Identity | Done
Core Infrastructure | Verify Function App Deployment | Done
Storage | Configure Storage Security | Done
Storage | Enable TLS 1.2 | Done
Storage | Enable Secure Transfer | Done
Storage | Configure Encryption | Done
OAuth / Entra ID | Create docproc-ingest-api App Registration | Done
OAuth / Entra ID | Create docproc-mule-client App Registration | Done
OAuth / Entra ID | Configure Application ID URI | Done
OAuth / Entra ID | Create Custom API Scope | Done
OAuth / Entra ID | Create App Role (DocProc.Submit) | Done
OAuth / Entra ID | Add API Permissions | Done
OAuth / Entra ID | Grant Admin Consent | Pending
RBAC | Assign Managed Identity Storage Roles | Pending
RBAC | Assign Service Bus Roles | Pending
RBAC | Assign Key Vault Roles | Pending
RBAC | Assign Cognitive Services Roles | Pending
Azure Resources | Create Service Bus Namespace | Pending
Azure Resources | Create Azure SQL Database | Pending
Azure Resources | Create Key Vault | Pending
Azure Resources | Create Azure OpenAI Resource | Pending
Azure Resources | Create Document Intelligence Resource | Pending
Document Intelligence | Train Custom Classifier | Pending
Document Intelligence | Train EV Extractor | Pending
Application Development | Deploy Ingest Function Code | Pending
Application Development | Deploy Classifier Function Code | Pending
Application Development | Deploy Employment Function Code | Pending
Application Development | Deploy Identity Function Code | Pending
Application Development | Deploy Aggregator Function Code | Pending
Testing | OAuth Testing | Pending
Testing | Managed Identity Testing | Pending
Testing | Service Bus Testing | Pending
Testing | SQL Testing | Pending
Testing | End-to-End Testing | Pending
Testing | Mule Integration Testing | Pending